## Sheet1
Codes | Descriptions | Minimum Duration | Expected Duration | Maximum Duration | Predecessors | Successors | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critical
Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | 1.581e-13 | 1.581e-13 | TRUE
A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 14.6857 | 1.581e-13 | 14.6857 | TRUE
A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 14.6857 | 18.6765 | 17.6328 | 21.6236 | FALSE
A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 14.6857 | 19.8284 | 16.4809 | 21.6236 | FALSE
A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 14.6857 | 21.6236 | 14.6857 | 21.6236 | TRUE
B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 21.6236 | 25.5199 | 21.6236 | 25.5199 | TRUE
B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 25.5199 | 29.8197 | 30.62 | 34.9197 | FALSE
B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 25.5199 | 32.0157 | 28.424 | 34.9197 | FALSE
B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 25.5199 | 34.9197 | 25.5199 | 34.9197 | TRUE
C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 34.9197 | 39.8722 | 34.9197 | 39.8722 | TRUE
C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 39.8722 | 43.7329 | 43.2921 | 47.1528 | FALSE
C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 39.8722 | 47.1528 | 39.8722 | 47.1528 | TRUE
D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 47.1528 | 51.7738 | 47.1528 | 51.7738 | TRUE
D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 51.7738 | 58.1632 | 51.7738 | 58.1632 | TRUE
D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 58.1632 | 77.6013 | 58.1632 | 77.6013 | TRUE
E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 77.6013 | 97.8848 | 77.6013 | 97.8848 | TRUE
E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 97.8848 | 114.6489 | 121.1581 | 137.9221 | FALSE
E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 97.8848 | 137.9221 | 97.8848 | 137.9221 | TRUE
F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 137.9221 | 158.3701 | 137.9221 | 158.3701 | TRUE
F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 158.3701 | 162.1121 | 161.9816 | 165.7236 | FALSE
F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 158.3701 | 163.6723 | 160.4213 | 165.7236 | FALSE
F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 158.3701 | 164.497 | 159.5967 | 165.7236 | FALSE
F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 158.3701 | 165.7236 | 158.3701 | 165.7236 | TRUE
G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 165.7236 | 173.2162 | 165.7236 | 173.2162 | TRUE
G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 173.2162 | 175.6983 | 177.367 | 179.849 | FALSE
G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 173.2162 | 176.548 | 176.5172 | 179.849 | FALSE
G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 173.2162 | 178.9727 | 174.0925 | 179.849 | FALSE
G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 173.2162 | 179.849 | 173.2162 | 179.849 | TRUE
H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 179.849 | 187.5923 | 179.849 | 187.5923 | TRUE
H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 187.5923 | 190.9578 | 192.21 | 195.5755 | FALSE
H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 187.5923 | 195.5755 | 187.5923 | 195.5755 | TRUE
I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 195.5755 | 199.493 | 201.735 | 205.6525 | FALSE
I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 195.5755 | 202.2214 | 199.0066 | 205.6525 | FALSE
I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 195.5755 | 205.6525 | 195.5755 | 205.6525 | TRUE
J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 205.6525 | 222.555 | 216.9308 | 233.8332 | FALSE
J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 205.6525 | 233.8332 | 205.6525 | 233.8332 | TRUE
J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 233.8332 | 255.7036 | 233.8332 | 255.7036 | TRUE
K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 255.7036 | 274.2269 | 255.7036 | 274.2269 | TRUE
L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 274.2269 | 277.2104 | 301.402 | 304.3855 | FALSE
L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 274.2269 | 279.1684 | 299.444 | 304.3855 | FALSE
L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 274.2269 | 285.7385 | 292.8739 | 304.3855 | FALSE
L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 274.2269 | 287.1051 | 291.5073 | 304.3855 | FALSE
L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 274.2269 | 288.7527 | 289.8597 | 304.3855 | FALSE
L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 274.2269 | 301.2708 | 277.3416 | 304.3855 | FALSE
L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 274.2269 | 304.3855 | 274.2269 | 304.3855 | TRUE
M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 304.3855 | 311.1054 | 304.3855 | 311.1054 | TRUE
M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 311.1054 | 318.3563 | 319.7153 | 326.9662 | FALSE
M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 311.1054 | 318.7807 | 319.291 | 326.9662 | FALSE
M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 311.1054 | 326.9662 | 311.1054 | 326.9662 | TRUE
N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 326.9662 | 335.7181 | 326.9662 | 335.7181 | TRUE
N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 335.7181 | 351.7285 | 335.7181 | 351.7285 | TRUE
O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 351.7285 | 355.9121 | 362.636 | 366.8196 | FALSE
O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 351.7285 | 356.6193 | 361.9289 | 366.8196 | FALSE
O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 351.7285 | 366.8196 | 351.7285 | 366.8196 | TRUE
O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 366.8196 | 370.8302 | 366.9958 | 371.0063 | FALSE
O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 366.8196 | 371.0063 | 366.8196 | 371.0063 | TRUE
P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 371.0063 | 373.5319 | 373.5711 | 376.0966 | FALSE
P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 371.0063 | 375.7333 | 371.3697 | 376.0966 | FALSE
P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 371.0063 | 376.0966 | 371.0063 | 376.0966 | TRUE
Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 376.0966 | 379.9172 | 376.0966 | 379.9172 | TRUE
Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 379.9172 | 383.0937 | 379.9172 | 383.0937 | TRUE
Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 383.0937 | 384.0937 | 383.0937 | 384.0937 | TRUE
Completion |  | 0 | 0 | 0 | Q.3 |  | 384.0937 | 384.0937 | 384.0937 | 384.0937 | TRUE