## Sheet1
Codes | Descriptions | Minimum Duration | Expected Duration | Maximum Duration | Predecessors | Successors | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critical
Start |  | 0 | 0 | 0 |  | A, B | 0 | 0 | 0 | 0 | TRUE
B | Preparation of the ground | 1 | 2 | 4 | Start | D | 0 | 2.8095 | 5.5378 | 8.3473 | FALSE
A | Agreement of the owner | 3 | 4 | 6 | Start | C, D, E | 0 | 5.0432 | 0 | 5.0432 | TRUE
C | Order of materials | 1 | 1 | 3 | A | F | 5.0432 | 6.317 | 6.0986 | 7.3725 | FALSE
D | Excavation | 1 | 1 | 3 | A, B | G | 5.0432 | 6.6226 | 8.3473 | 9.9266 | FALSE
E | Order of doors and windows | 1 | 2 | 4 | A | H | 5.0432 | 7.2258 | 5.0432 | 7.2258 | TRUE
F | Delivery of materials | 1 | 2 | 4 | C | G | 6.317 | 8.8712 | 7.3725 | 9.9266 | FALSE
G | Concrete foundations | 1 | 2 | 4 | D, F | J | 8.8712 | 11.7453 | 9.9266 | 12.8007 | FALSE
J | Frame, roofs, walls | 3 | 4 | 6 | G | K | 11.7453 | 15.0369 | 12.8007 | 16.0923 | FALSE
H | Delivery of doors and windows | 8 | 10 | 12 | E | K | 7.2258 | 16.0923 | 7.2258 | 16.0923 | TRUE
K | Installation of doors and windows | 1 | 1 | 3 | H, J | End | 16.0923 | 18.2818 | 16.0923 | 18.2818 | TRUE
End |  | 0 | 0 | 0 | K |  | 18.2818 | 18.2818 | 18.2818 | 18.2818 | TRUE