## Sheet1
Codes | Descriptions | Minimum Duration | Expected Duration | Maximum Duration | Predecessors | Successors | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critical
Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | 0 | 0 | TRUE
A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 12 | 0 | 12 | TRUE
A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 12 | 18 | 12 | 18 | TRUE
A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 12 | 18 | 12 | 18 | TRUE
A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 12 | 16 | 14 | 18 | FALSE
B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 18 | 22 | 18 | 22 | TRUE
B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 22 | 28 | 24 | 30 | FALSE
B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 22 | 30 | 22 | 30 | TRUE
B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 22 | 28 | 24 | 30 | FALSE
C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 30 | 38 | 30 | 38 | TRUE
C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 38 | 44 | 38 | 44 | TRUE
C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 38 | 42 | 40 | 44 | FALSE
D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 44 | 48 | 44 | 48 | TRUE
D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 48 | 60 | 48 | 60 | TRUE
D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 60 | 80 | 60 | 80 | TRUE
E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 80 | 98 | 80 | 98 | TRUE
E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 98 | 118 | 108 | 128 | FALSE
E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 98 | 128 | 98 | 128 | TRUE
F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 128 | 144 | 128 | 144 | TRUE
F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 144 | 150 | 150 | 156 | FALSE
F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 144 | 156 | 144 | 156 | TRUE
F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 144 | 150 | 150 | 156 | FALSE
F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 144 | 148 | 152 | 156 | FALSE
G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 156 | 164 | 156 | 164 | TRUE
G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 164 | 172 | 164 | 172 | TRUE
G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 164 | 170 | 166 | 172 | FALSE
G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 164 | 168 | 168 | 172 | FALSE
G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 164 | 168 | 168 | 172 | FALSE
H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 172 | 180 | 172 | 180 | TRUE
H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 180 | 188 | 180 | 188 | TRUE
H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 180 | 184 | 184 | 188 | FALSE
I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 188 | 200 | 188 | 200 | TRUE
I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 188 | 196 | 192 | 200 | FALSE
I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 188 | 192 | 196 | 200 | FALSE
J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 200 | 232 | 200 | 232 | TRUE
J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 200 | 228 | 204 | 232 | FALSE
J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 232 | 250 | 232 | 250 | TRUE
K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 250 | 268 | 250 | 268 | TRUE
L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 268 | 296 | 268 | 296 | TRUE
L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 268 | 284 | 280 | 296 | FALSE
L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 268 | 276 | 288 | 296 | FALSE
L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 268 | 272 | 292 | 296 | FALSE
L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 268 | 272 | 292 | 296 | FALSE
L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 268 | 284 | 280 | 296 | FALSE
L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 268 | 292 | 272 | 296 | FALSE
M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 296 | 302 | 296 | 302 | TRUE
M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 302 | 314 | 302 | 314 | TRUE
M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 302 | 310 | 306 | 314 | FALSE
M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 302 | 308 | 308 | 314 | FALSE
N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 314 | 322 | 314 | 322 | TRUE
N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 322 | 340 | 322 | 340 | TRUE
O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 340 | 344 | 348 | 352 | FALSE
O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 340 | 352 | 340 | 352 | TRUE
O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 340 | 344 | 348 | 352 | FALSE
O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 352 | 356 | 352 | 356 | TRUE
O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 352 | 356 | 352 | 356 | TRUE
P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 356 | 360 | 358 | 362 | FALSE
P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 356 | 362 | 356 | 362 | TRUE
P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 356 | 360 | 358 | 362 | FALSE
Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 362 | 366 | 362 | 366 | TRUE
Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 366 | 370 | 366 | 370 | TRUE
Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 370 | 371 | 370 | 371 | TRUE
Completion |  | 0 | 0 | 0 | Q.3 |  | 371 | 371 | 371 | 371 | TRUE