## Sheet1
Codes | Descriptions | Minimum Duration | Expected Duration | Maximum Duration | Predecessors | Successors | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critical
Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | 0 | 0 | TRUE
A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 18 | 0 | 18 | TRUE
A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 18 | 27 | 18 | 27 | TRUE
A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 18 | 27 | 18 | 27 | TRUE
A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 18 | 24 | 21 | 27 | FALSE
B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 27 | 33 | 27 | 33 | TRUE
B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 33 | 42 | 36 | 45 | FALSE
B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 33 | 45 | 33 | 45 | TRUE
B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 33 | 42 | 36 | 45 | FALSE
C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 45 | 57 | 45 | 57 | TRUE
C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 57 | 66 | 57 | 66 | TRUE
C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 57 | 63 | 60 | 66 | FALSE
D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 66 | 72 | 66 | 72 | TRUE
D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 72 | 90 | 72 | 90 | TRUE
D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 90 | 120 | 90 | 120 | TRUE
E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 120 | 147 | 120 | 147 | TRUE
E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 147 | 177 | 162 | 192 | FALSE
E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 147 | 192 | 147 | 192 | TRUE
F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 192 | 216 | 192 | 216 | TRUE
F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 216 | 225 | 225 | 234 | FALSE
F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 216 | 234 | 216 | 234 | TRUE
F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 216 | 225 | 225 | 234 | FALSE
F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 216 | 222 | 228 | 234 | FALSE
G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 234 | 246 | 234 | 246 | TRUE
G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 246 | 258 | 246 | 258 | TRUE
G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 246 | 255 | 249 | 258 | FALSE
G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 246 | 252 | 252 | 258 | FALSE
G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 246 | 252 | 252 | 258 | FALSE
H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 258 | 270 | 258 | 270 | TRUE
H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 270 | 282 | 270 | 282 | TRUE
H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 270 | 276 | 276 | 282 | FALSE
I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 282 | 300 | 282 | 300 | TRUE
I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 282 | 294 | 288 | 300 | FALSE
I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 282 | 288 | 294 | 300 | FALSE
J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 300 | 348 | 300 | 348 | TRUE
J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 300 | 342 | 306 | 348 | FALSE
J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 348 | 375 | 348 | 375 | TRUE
K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 375 | 402 | 375 | 402 | TRUE
L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 402 | 444 | 402 | 444 | TRUE
L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 402 | 426 | 420 | 444 | FALSE
L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 402 | 414 | 432 | 444 | FALSE
L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 402 | 408 | 438 | 444 | FALSE
L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 402 | 408 | 438 | 444 | FALSE
L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 402 | 426 | 420 | 444 | FALSE
L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 402 | 438 | 408 | 444 | FALSE
M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 444 | 453 | 444 | 453 | TRUE
M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 453 | 471 | 453 | 471 | TRUE
M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 453 | 465 | 459 | 471 | FALSE
M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 453 | 462 | 462 | 471 | FALSE
N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 471 | 483 | 471 | 483 | TRUE
N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 483 | 510 | 483 | 510 | TRUE
O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 510 | 516 | 522 | 528 | FALSE
O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 510 | 528 | 510 | 528 | TRUE
O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 510 | 516 | 522 | 528 | FALSE
O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 528 | 534 | 528 | 534 | TRUE
O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 528 | 534 | 528 | 534 | TRUE
P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 534 | 540 | 537 | 543 | FALSE
P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 534 | 543 | 534 | 543 | TRUE
P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 534 | 540 | 537 | 543 | FALSE
Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 543 | 549 | 543 | 549 | TRUE
Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 549 | 555 | 549 | 555 | TRUE
Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 555 | 556 | 555 | 556 | TRUE
Completion |  | 0 | 0 | 0 | Q.3 |  | 556 | 556 | 556 | 556 | TRUE