## Sheet1
Codes | Descriptions | Minimum Duration | Expected Duration | Maximum Duration | Predecessors | Successors | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critical
Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | 0 | 0 | TRUE
A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 6 | 0 | 6 | TRUE
A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 6 | 9 | 6 | 9 | TRUE
A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 6 | 9 | 6 | 9 | TRUE
A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 6 | 8 | 7 | 9 | FALSE
B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 9 | 11 | 9 | 11 | TRUE
B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 11 | 14 | 12 | 15 | FALSE
B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 11 | 15 | 11 | 15 | TRUE
B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 11 | 14 | 12 | 15 | FALSE
C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 15 | 19 | 15 | 19 | TRUE
C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 19 | 22 | 19 | 22 | TRUE
C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 19 | 21 | 20 | 22 | FALSE
D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 22 | 24 | 22 | 24 | TRUE
D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 24 | 30 | 24 | 30 | TRUE
D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 30 | 40 | 30 | 40 | TRUE
E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 40 | 49 | 40 | 49 | TRUE
E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 49 | 59 | 54 | 64 | FALSE
E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 49 | 64 | 49 | 64 | TRUE
F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 64 | 72 | 64 | 72 | TRUE
F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 72 | 75 | 75 | 78 | FALSE
F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 72 | 78 | 72 | 78 | TRUE
F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 72 | 75 | 75 | 78 | FALSE
F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 72 | 74 | 76 | 78 | FALSE
G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 78 | 82 | 78 | 82 | TRUE
G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 82 | 86 | 82 | 86 | TRUE
G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 82 | 85 | 83 | 86 | FALSE
G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 82 | 84 | 84 | 86 | FALSE
G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 82 | 84 | 84 | 86 | FALSE
H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 86 | 90 | 86 | 90 | TRUE
H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 90 | 94 | 90 | 94 | TRUE
H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 90 | 92 | 92 | 94 | FALSE
I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 94 | 100 | 94 | 100 | TRUE
I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 94 | 98 | 96 | 100 | FALSE
I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 94 | 96 | 98 | 100 | FALSE
J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 100 | 116 | 100 | 116 | TRUE
J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 100 | 114 | 102 | 116 | FALSE
J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 116 | 125 | 116 | 125 | TRUE
K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 125 | 134 | 125 | 134 | TRUE
L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 134 | 148 | 134 | 148 | TRUE
L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 134 | 142 | 140 | 148 | FALSE
L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 134 | 138 | 144 | 148 | FALSE
L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 134 | 136 | 146 | 148 | FALSE
L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 134 | 136 | 146 | 148 | FALSE
L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 134 | 142 | 140 | 148 | FALSE
L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 134 | 146 | 136 | 148 | FALSE
M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 148 | 151 | 148 | 151 | TRUE
M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 151 | 157 | 151 | 157 | TRUE
M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 151 | 155 | 153 | 157 | FALSE
M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 151 | 154 | 154 | 157 | FALSE
N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 157 | 161 | 157 | 161 | TRUE
N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 161 | 170 | 161 | 170 | TRUE
O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 170 | 172 | 174 | 176 | FALSE
O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 170 | 176 | 170 | 176 | TRUE
O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 170 | 172 | 174 | 176 | FALSE
O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 176 | 178 | 176 | 178 | TRUE
O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 176 | 178 | 176 | 178 | TRUE
P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 178 | 180 | 179 | 181 | FALSE
P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 178 | 181 | 178 | 181 | TRUE
P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 178 | 180 | 179 | 181 | FALSE
Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 181 | 183 | 181 | 183 | TRUE
Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 183 | 185 | 183 | 185 | TRUE
Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 185 | 186 | 185 | 186 | TRUE
Completion |  | 0 | 0 | 0 | Q.3 |  | 186 | 186 | 186 | 186 | TRUE