## Sheet1
Codes | Descriptions | Minimum Duration | Expected Duration | Maximum Duration | Predecessors | Successors | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critical
Start |  | 0 | 0 | 0 |  | A, B | 0 | 0 | 0 | 0 | TRUE
A | Agreement of the owner | 3 | 4 | 6 | Start | C, D, E | 0 | 6 | 0 | 6 | TRUE
B | Preparation of the ground | 1 | 2 | 4 | Start | D | 0 | 4 | 6 | 10 | FALSE
C | Order of materials | 1 | 1 | 3 | A | F | 6 | 9 | 6 | 9 | TRUE
D | Excavation | 1 | 1 | 3 | A, B | G | 6 | 9 | 10 | 13 | FALSE
E | Order of doors and windows | 1 | 2 | 4 | A | H | 6 | 10 | 7 | 11 | FALSE
F | Delivery of materials | 1 | 2 | 4 | C | G | 9 | 13 | 9 | 13 | TRUE
G | Concrete foundations | 1 | 2 | 4 | D, F | J | 13 | 17 | 13 | 17 | TRUE
H | Delivery of doors and windows | 8 | 10 | 12 | E | K | 10 | 22 | 11 | 23 | FALSE
J | Frame, roofs, walls | 3 | 4 | 6 | G | K | 17 | 23 | 17 | 23 | TRUE
K | Installation of doors and windows | 1 | 1 | 3 | H, J | End | 23 | 26 | 23 | 26 | TRUE
End |  | 0 | 0 | 0 | K |  | 26 | 26 | 26 | 26 | TRUE